## Slide 1: Quote
Project Charter/
What is the background, the objective and the benefit?
Project name
Indonesia Folding Crane Market Strategy: one challenger crane for every tm class
Background
• Hyva has stopped making cranes: 102 Hyva cranes (Rp 36,1 Bio) sold in 2023 – 2026 need a new brand
• Indonesia imports ~188 folding cranes a year (Rp 100,2 Bio) across all four classes
Objective
Sell 15 folding cranes by December 2027
• 4C: map all 636 imported folding cranes (Rp 321,8 Bio, 2023 – 2026) by class, brand, model
• STP: split into 16 tm classes and find the top 1 model in each
• 4P: set a cheaper F.lli Ferrari or XCMG challenger per tm class (8 of 16 done)
Project Scope
• In: folding cranes, Light to Heavy; price and specification; imports 2023 – 2026
• Out: telescopic, grabber and forestry cranes; Hyva; Zoomlion
KPI / Metric
Units sold | 15 cranes | by Dec 2027
Revenue | ≈ Rp 14,1 Bio | GP ≈ Rp 5,0 Bio (35%)
Cost vs leader | Rp 21 – 625 Jt lower | per unit, in 8 of 16 tm classes
Lead time | ≤ 14 weeks | stock in Malaysia (TBC)
Support Requirements
• Business Consultant: leads, customer visits · Marcom: sales kit, exhibitions
• Application Engineering: tm class, specs · UTPE: quotation, mounting, install
Project Timeframe
Activity
2026
2027
J
J
A
S
O
N
D
J
F
M
A
M
J
J
A
S
O
N
D
Market study (4C)
STP & challenger choice
Negotiate F.lli Ferrari & XCMG
Sales kit with Marcom
Exhibition & customer visits
Quotation → PO → delivery
15 cranes sold
★
Benefit of Project
• ≈ Rp 14,1 Bio revenue, Rp 5,0 Bio GP from 15 cranes by end-2027
• Replaces Hyva: ~33 cranes a year get a new brand
• Our cost is Rp 21 – 625 Jt below the leader per unit: room for 35% GP
• Lead time ≤ 14 weeks (China / Malaysia) vs 25 – 27 weeks (Italy / Brazil)
Project Team
Executive Sponsor
Advisor
Owner
Coordinator
Project Lead
Team Member
: David
: Ceisar Centiaga
: Ricardo Tanada
: Ignatius Indrawan Sumawinata
: Tiberias Krisgaharu Simu
: Business Consultant, Application Engineering, Marcom, UTPE
Project Approval
Lead
Date:
Tiberias K. Simu
Coordinator
Date:
Ignatius Indrawan S.
Owner
Date:
Ricardo Tanada
Advisor
Date:
Ceisar Centiaga
Executive Sponsor
Date:
David
Revenue plan, 15 cranes: 10 XCMG (SQ3.2ZK2 ×5, SQZ325.4 ×2, KSQZ365.4 ×2, GSQZ200.3 ×1) + 5 F.lli Ferrari FBR450 A4; selling price = cost ÷ (1 − 35% GP). Prices and units from the crane market slides (imports 2023 – 2026, F.lli Ferrari price list June 2026). Lead time per F.lli Ferrari price list; Malaysia stock to be confirmed.